Nicola Valley Community Arts Council           https//:nicolavalleyartscouncil.com

nvcac.talent@gmail.com

Attention: Artists, Musicians, Artisans, Writers, Poets, Actors and all other talented folks

We are creating a “Talent Network” to find and promote all the talented people in the Nicola Valley area.

The plan is to create a database of information about the skills and interests that we want to share, whether as a business or a hobby.  This growing information set will be a treasure when looking for someone to perform at an event, create a commissioned work, teach a skill, find an instructor, or find others with your interests.

This project has several steps, each with different needs for data, funding, volunteer assistance and decisions.

- Design and Start-up (Dec 2018-Feb 2019)

  - Data: 		Basic concept work, spreadsheet planning, application form, logo,

  - Funding: 	“new program” funding from the Nicola Valley Community Arts Council

  - Volunteers: 	Basic spreadsheet creation, application form, logo creation, recruitment planning

  - Decision: 	Is this a viable project that could fulfill the objectives? Stop or go?

- Implement (Mar-May 2019)

  - Data: 		build database from applications, implement social media plan, website, invitations

  - Funding: 	funding from NVCAC and City of Merritt, plan for ongoing financial stability

  - Volunteers: 	distribute application forms, social media, promotional events

  - Decision:	Is there sufficient interest to create a viable database (minimum 100). Stop or go?

- Manage (June-Aug 2019)

  - Data: 		continue to collect and add applications, create online resources

  - Funding: 	membership fees and grants

  - Volunteers: 	promotion via social media and community events

  - Decision: 	set 2020 membership fee for ongoing support

Interested?

Info and application forms for the Talent Network are on the NVCAC website and at the Courthouse Arts Centre.